## Sheet1
Company Management System | [6 empty] | Project Overview: The Main Goal is to develop a website that make it more easy to manage your company and employees with also services to organize the work progress
Group Members
|  | Developer Name |  | Roles
| 1 | Ahed Akrout |  | Team Leader - Backend
| 2 | Melad Mustafabadran |  | Frontend
| 3 | Beste Ozkan |  | Designer
| 4 | Osamah Naji |  | Tester
| Project Progress | [6 empty] | Resources
|  | Mission | Responsible |  | Deadline | Status / Date |  | Product | Budget
| 1 | Project Requirements Analysis | Ahed - Melad |  | 2026-02-25 | In Progress
| 2 | UI/UX Design | Beste |  | 2026-03-01 | In Progress
| 3 | Website Pages Development | Melad |  | 2026-03-20 | To Do
| 4 | Backend API Development | Ahed |  | 2026-04-10 | To Do
| 5 | Database Implementation | Ahed |  | 2026-04-20 | To Do
| 6 | System Testing | Osamah |  | 2026-04-25 | To Do |  | Total Budget: | 0$
| 7 | Bug Fixing | Melad - Ahed |  | 2026-05-01 | To Do
| 8 | Documentation | All Members |  | 2026-05-05 | To Do
Note on P16: Melad Mustafabadran: Not Needed Yet